## UAT
User Acceptance Test Plan
Project Name |  | Haukainga - Home Winds
Project Client |  | Huia Te Kanua
Name of Tester/s: |  | Charlie
Test ID | Description of test cases | Steps To Execute | Test data | Expected Results/Behaviour | Observed Results/Behaviour | Pass/Fail | Defect/Comments/Additions
1 | Verify navigation bar links work correctly. | Open the website to the homepage. Click HOME, WATCHES, ABOUT, CONTACT US, and ORDERS. | Navigation menu links. | Each menu option should navigate to the correct page or section without broken links or loading issues. | Links successfully took the user to the intended pages. | PASS | The navigation menu is clear, responsive, and easy to use.
2 | Verify watch products display correctly. | Open the website to the homepage. Scroll down to the latest watches section. Click on different smartwatch product cards. Observe the behaviour after selection. | Smartwatch product cards from the Latest Watches section. | When the user clicks a product card the website should either display product details or navigate to a dedicated product page without errors. | Clicking a watch product card did not display additional product information or open a product page. Instead, the site returned to the main homepage/appeared to refresh. | FAIL | The product cards appear clickable but don’t actually provide any additional function. The corrective action to take would be implementing a working link or disable the clickable behaviour.
3 | Verify contact form accepts user input. | Open the website to the homepage. Scroll down to the Contact Us section. Enter sample information into all fields. Click Send. | Full Name: Charlie Marett Email: charlie@email.com Phone: 0211234567 Message: Interested in purchasing a smartwatch. | The form should successfully process the submission and display a success/confirmation message without any errors. | The form accepted the entered data, however, after pressing send the page returned to the homepage/appeared to refresh. No confirmation message was displayed to indicate that the form was successfully processed. | FAIL | The contact form appears to lack backend processing or user feedback functionality. The corrective action to take would be to implement form handling and add a confirmation/success message after submission.
4 | Verify page layout and interface remain usable during scrolling and browsing. | Open the website to the homepage. Scroll from top to bottom. Observe the alignment of sections, buttons, images, and text. | Website interface elements. | The page content should remain readable, aligned, and visually consistent across the site. | The sections loaded correctly. Images, buttons, text blocks, and product cards remained aligned during navigation. | PASS | UI design is consistent across sections and provides a professional appearance.
5 | Verify the functionality of the footer Google Maps link and email subscription feature. | Open the website to the homepage. Scroll down to the website's footer. Click the Google Maps icon. Observe the website's behaviour. Enter an email address into the Subscribe field. Click Subscribe. Check whether confirmation or subscription feedback is displayed. | Email: test@gmail.com | The Google Maps feature should provide location access or map functionality. The Subscribe feature should process the email submission and display a confirmation message or successful subscription notification. | Clicking the Google Maps section redirected the user to the external Google Maps website. Entering an email and clicking Subscribe caused the user to return to the top of the homepage. After navigating back to the footer, the entered email remained in the field, however there was no confirmation message or indication that the subscription had been successfully processed. | FAIL | The subscription feature lacks user feedback and clear submission confirmation. The corrective action to take would be to implement a confirmation message and verify whether email submissions are being processed correctly.
6 | Verify the homepage Contact Us button functions correctly. | Open the homepage. Locate the Contact Us button in the banner section. Click the button. Observe website behaviour. | Homepage Contact Us button. | The button should redirect the user to the Contact Us section or dedicated contact page. | Clicking the Contact Us button produced no response. The user remained on the same section of the homepage. | FAIL | The button appears interactive but currently has no implemented functionality. The corrective action to take would be connecting the button to the Contact Us section or appropriate webpage destination.
7 | Verify the footer social media icons function correctly. | Scroll to the website footer. Click each available social media icon. Observe page behaviour. | Social media icons (Facebook, Twitter, LinkedIn, Instagram). | Each icon should redirect the user to the relevant social media page or external profile. | Clicking the social media icons produced no response. No external pages opened and the user remained on the current webpage. | FAIL | Social media icons appear available but currently lack active links or implemented functionality. The corrective action to take would be adding working social media URLs or remove inactive icons.
8 | Verify users can access all homepage content sections successfully. | Open the homepage. Scroll from the top banner to the footer. Review all major website sections. | Homepage sections. | Users should be able to access all content areas without broken layout, missing sections, or navigation problems. | All homepage sections loaded and were accessible during scrolling. Content, images, and layout displayed correctly. | PASS | Website content remained readable and organised throughout navigation.
9 | Verify testimonial navigation controls rotate customer testimonials correctly. | Scroll to the Testimonial section. Click the testimonial navigation arrow buttons multiple times. Observe displayed testimonial content. | Testimonial navigation controls. | The testimonial section should cycle through multiple customer reviews without repetition issues. | The testimonial controls functioned and rotated content successfully, however the section only cycled between the same two testimonials repeatedly. | PASS | Feature is functional but contains limited testimonial variety. The improvement to make would be expanding the testimonial content to improve user experience.
10 | Verify the buttons on the Orders page function correctly. | Navigate to the Orders page. Click View Order. Click Track Shipment. Click Buy It Again. Click Request a Return. Observe website behaviour after each interaction. | Orders page buttons. | Each button should perform its intended action, such as: View Order → display order details. Track Shipment → provide shipment tracking information. Buy It Again → begin repurchasing the product. Request a Return → open the return request process. | The Orders page loaded successfully and displayed order information correctly. However, clicking View Order, Track Shipment, Buy It Again, and Request a Return produced no response and no additional pages, pop-ups, or actions were triggered. | FAIL | The Orders page buttons appear interactive but currently lack implemented functionality. The corrective action to take would be connecting the buttons to their intended workflows or disable inactive controls until functionality is available.

## UAT Example
User Acceptance Test Plan
Project Name |  | Haukainga - Home Winds
Project Client |  | Huia Te Kanua
Name of Tester/s: |  | AgentBob
Test ID | Description of test cases | Steps To Execute | Test data | Expected Results/Behaviour | Observed Results/Behaviour | Pass/Fail | Defect/Comments/Additions
COMPONENT/MODULE 1: |  | Base WordPress and Plugins
1 | WordPress Plugin and Theme functionality | Install plugins and selected theme. Test plugin features and theme design. See if plugin features are successfully connected and modifying the database records. | - | Plugins perform as required and intereact with the database as required. Theme appears as expected and can be modified easily.
2 | Administrator login and features | Create two administrator accounts with identical privilages for dual development | - | Both administrator accounts have access to all WordPress and plugin features as well as a database accessbility.
3 | User roles and restrictions | Generate a login form to create standard users, as well as appoint property users via an admin interface. Using plugin content restriction, hide property management from standard users. | - | Standard users and property users can be created. Standard users cannot interact with property management.
4
COMPONENT/MODULE 2: |  | Custom Plugin Functionality
1 | Database Queries | Create test functions and test data to perform Insert, Updates, and Deletes on the user, property, booking, and review table. Perform DML statements in the order of Insert, Update, then Delete, ensuring all test data is deleted before continueing. | Single entries for each table defined within test functions | Database entries are modified as requested, and test functions return true. Test data is no longer present in the database
2 | HTTP Requests | Create an HTML form with a POST method. Retrieve this data with PHP then display this data. | Form entries with varied inputs such as special characters or SQL statements | All data retrieved is equal to what was given. Any special cases including SQL statements are converted to plain string.
3 | File Uploads | Create an HTML form to upload only images files, uploading these to a file as well as stored via hash function in the database. Display this image on screen after upload and storage. | Only image file types | Only accepts files of a certain type as size. Images are stored correctly and can be retrieved and displayed.
4 | Property and Review Read | Display a single property as well as all reviews and details. Display all propertys with brief information and no reviews. | Test Properties and reviews | All properties are viewed and can be filter as a list view. Individual properties can be viewed and display all reviews and information in a separate view.
5
COMPONENT/MODULE 3: |  | UI & UX
1 | Accessibility | Design each wordpress page and view to be accessible on any device prioritising PC and smart phone resolutions. | - | Pages change appropriately maintaining their theme and general appearance
2 | Read Data Appearance | Display retrieved data showing all information, data display is reformatted when the display viewport changes. | - | Data shown is correct and in full. Display adheres to chosen theme and general appearance.
3 | Links | Develop all links in an obvious and understandable manner. | - | All links operate as expected, redirecting to the correct location or displaying the correct information. Links purpose is made obvious to the average user.
4
5