## Color
PROJECT: Beerus
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project start date: | 2026-02-10 | 2026-02-10 |  |  |  | February | [20 empty] | March | [34 empty] | April | [27 empty] | May | [27 empty] | June
Scrolling increment: | 0 | time axis 2026-02-10 to 2026-07-01
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2026-02-10 to 2026-07-01
Iteration 1
Task 1: Group Meeting 1 | On Track | Everyone | 100% | 2026-02-10 | 1
Task 2: Create Stakeholders | On Track | Everyone | 100% | 2026-02-17 | 7
Task 3: Group Meeting 2 | On Track | Everyone | 100% | 2026-02-17 | 1
Task 4: Create Personas | On Track | Everyone | 100% | 2026-02-18 | 7
Task 5: Group Meeting 3 | On Track | Everyone | 100% | 2026-02-24 | 6
Iteration 2
Task 1: Weekly Meetings (Wks 5-9) | On Track | Everyone | 100% | 2026-03-10 | 42
Task 2: Gantt Chart | On Track | Joshua, Cameron | 100% | 2026-03-10 | 14
Task 3: GitHub Kanban Board | On Track | Everyone | 100% | 2026-03-17 | 7
Task 4: Resource Requirement List | On Track | Charlie | 100% | 2026-03-24 | 14
Task 5: Test & Review Changes on GitHub | On Track | Everyone | 100% | 2026-04-14 | 7
Iteration 3
Task 1: Weekly Meetings (Wks 9-12) | On Track | Everyone | 100% | 2026-04-21 | 21
Task 2: Risk Register | On Track | Charlie | 100% | 2026-04-21 | 14
Task 3: Merge Website Files | On Track | Everyone | 100% | 2026-05-05 | 7
Task 4: Publish Website via GitHub Pages | On Track | Joshua | 100% | 2026-05-12 | 5
Task 5: User Acceptance Testing | On Track | Everyone | 100% | 2026-05-19 | 7
To add more data, Insert new rows ABOVE this one